## README
Gateway Routing Table ¦ 작성 가이드
FreeRTOS CAN-LIN Gateway 프로젝트의 CAN↔LIN Signal Routing 규칙을 설계·리뷰·Freeze하기 위한 협업용 Excel 양식
1. Workbook Baseline
| Project | FreeRTOS CAN-LIN Gateway 7인 팀 프로젝트 | Gateway 설계 단계
| Purpose | CAN→LIN / LIN→CAN source → condition/conversion → destination Routing 규칙 정의 | Routing Table은 DBC/LDF 자체를 재정의하지 않음
| Reference | CAN-LIN Gateway Handbook v1.0 §8.3~8.5 / Project 시퀀스 Phase 4 | 현재 업로드된 CAN_Matrix.xlsx / LIN_Matrix.xlsx 참조
| Priority rule | 실제 최신 vehicle.dbc / vehicle.ldf / Matrix가 Handbook 예시보다 우선 | 충돌 시 먼저 충돌 사실 확인 후 수정
| Change rule | Interface 변경: Jira → Matrix/DBC/LDF → 상대 담당자 리뷰 필요 → Routing → FW/Tool/Test | Merge ≠ Done
| Review v0.3 | CAN→LIN 7개 항목 검토 완료 | C2L-001/002는 Review, C2L-003~007은 CAN source 부재로 Blocked. Freeze blocker는 Review_Summary 참조.
2. 권장 작성 순서
| 1 | Gateway 관련 Signal 추출 | DBC/LDF/Matrix에서 Gateway가 실제로 소비·생성하는 Signal만 식별
| 2 | CAN → LIN 작성 | CAN Source → 조건/변환 → LIN Destination 매핑
| 3 | LIN → CAN 작성 | LIN Source → 조건/변환 → CAN Destination 매핑
| 4 | Invalid/Timing 연계 | valid/stale/timeout 및 LIN Schedule/CAN Tx 정책 연결
| 5 | Signal Cache 필드 연결 | 최신 값, valid, timestamp/alive 상태를 보관할 Cache field 연결
| 6 | 상대 담당자 리뷰 | Interface 경계의 의미·방향·주기·conversion 합의
| 7 | Freeze 후 코드화 | routing_table.c/.h, RoutingTask, test case로 반영
3. 핵심 작성 규칙
| • | 한 행은 1개의 Source Signal → 1개의 Destination Signal route를 의미합니다.
| • | 동일 Source가 여러 Destination으로 가면 route를 여러 행으로 분리합니다.
| • | Routing Table에서 새로운 CAN/LIN Signal을 임의로 만들지 않습니다. 새 Signal이 필요하면 Interface Change 절차를 먼저 수행합니다.
| • | 조건/변환은 코드처럼 명확하게 적되, 근거 없는 임계값이나 timing 숫자를 새로 만들지 않습니다.
| • | LIN Destination은 최신 LDF Schedule과 연결하고, CAN Destination은 Cyclic/Event 정책과 연결합니다.
| • | OPEN/TBD Interface는 Routing도 OPEN/TBD로 남기고 확정처럼 작성하지 않습니다.
| • | CAN/LIN Interface 변경 관련 행은 반드시 상대 담당자 리뷰 필요입니다.
4. Status / Color Legend
| Blue text | 사용자가 직접 작성/수정하는 Routing 입력
| Green text | CAN/LIN Matrix에서 가져온 참고 데이터
| Gray | 고정값 / 예시 / 방향 상수
| Orange | 리뷰 필요 / Interface Change 주의
| Light red | Blocked / 오류 / 충돌
5. Route ID / Status 권장
| RT-C2L-### | CAN → LIN route
| RT-L2C-### | LIN → CAN route
| Draft | 작성 중
| Review | 상대 담당자/시스템 담당 리뷰 중
| Frozen | Interface Freeze 승인
| Blocked | Interface 미정/충돌로 보류
| EXAMPLE | 양식 설명용 예시 행

## Review_Summary
CAN→LIN Routing Review Summary ¦ v0.3
검토 기준: CAN_Matrix.xlsx, LIN_Matrix.xlsx, 메시지 정의서_v0.3, 기능 정의서, Handbook/Architecture. 실제 최신 DBC/LDF가 있으면 해당 산출물 우선.
ID | Severity | Affected Route | Finding | Why it matters | Required Action | Freeze Blocker | Review
REV-01 | HIGH | All C2L | LIN baseline 불일치: LIN_Matrix.xlsx는 BASE-20ms/Window TBD, 메시지 정의서_v0.3은 BODY_10ms/Window 0x14 등 Team Encoding 사용 | Routing slot/period가 어느 기준인지 확정되지 않으면 구현·PulseView 검증 기준이 달라짐 | LIN_Matrix/Schedule/LDF를 최신 Team Encoding과 1:1 동기화 후 리뷰 | YES | 상대 담당자 리뷰 필요
REV-02 | HIGH | C2L-002 | VCU_Command.Brake의 Invalid=1이 정상 TRUE=1과 동일 | 1-bit raw 값만으로 정상 Brake ON과 signal invalid를 구분할 수 없음 | CAN Interface에서 invalid 정책을 재정의. 예: message-level validity 사용 여부 또는 bit layout 변경을 Jira에서 결정 | YES | VCU + Gateway + CAN 담당
REV-03 | MEDIUM | C2L-001 | Gear 4~7 처리 불명확/문서 간 차이. 정상 정의는 P/N/D/R(0~3)뿐 | 기존 v0.2의 “기타 valid gear→0”은 OPEN/RESERVED 값을 정상값으로 오인 가능 | Routing은 0~3만 정상으로 허용하고 4~7은 invalid/reserved 경로로 처리. CAN Matrix/DBC 값 범위도 리뷰 | NO* | VCU + Gateway (*Freeze 전 source 정의는 정리 필요)
REV-04 | HIGH | C2L-003~007 | Head/Turn/Hazard/Door Lock/Window 명령의 CAN source Message/Signal이 현재 CAN_Matrix에 없음 | Destination LIN command는 있어도 CAN→LIN 입력이 없으므로 Routing 구현 불가 | 각 기능의 source ECU/Message/Signal을 정의하거나 CAN→LIN 범위에서 제외. 신규 Interface면 Jira→Matrix→DBC→리뷰 | YES | 상대 담당자 리뷰 필요
REV-05 | MEDIUM | All LIN destination | Frame ID와 Protected PID 표기가 혼재 | Gateway 저수준 LIN 구현에서는 실제 PID 확인이 필요하며 0x1x 값을 그대로 PID로 오해할 위험 | Routing Table에는 Frame ID와 PID를 구분하고, PID는 최신 LDF 기준으로 검증 | YES (implementation) | Gateway + LIN Common
REV-06 | HIGH | All | 현재 프로젝트 첨부 기준 vehicle.dbc / vehicle.ldf 최신본을 직접 대조하지 못함 | Matrix/메시지 정의서와 실제 DB 파일이 다르면 Routing bit/enum/slot이 틀릴 수 있음 | 최신 DBC/LDF와 Matrix diff 및 parse/encode/decode/LDF 검증 후 Freeze | YES | Gateway + CAN/LIN + PC/Test

## _LISTS (hidden)
Route Status | Interface Status | Conversion Type | Delivery Timing | Review Complete
Draft | Confirmed | Copy | On Cache Update | ☐
Review | Team Decision | Bool Copy | LIN Schedule Slot | ☑
Frozen | OPEN | Enum→Bool | CAN Cyclic
Blocked | TBD / OPEN | Enum Mapping | CAN Event
EXAMPLE | Needs Review | Scale | Periodic Snapshot
|  | Range Check | On Change
|  | Bitmask | TBD / OPEN
Fault Map
Custom Function

## CAN_to_LIN
Gateway Routing Table ¦ CAN → LIN
One row = one source signal → one destination signal route. DBC/LDF/Matrix 정의를 재설계하는 시트가 아니라, 확정된 Interface를 연결하는 Gateway 규칙을 관리합니다.
검토 기준: CAN_Matrix.xlsx + 메시지 정의서_v0.3 Team Encoding. 단, LIN_Matrix.xlsx는 구형 BASE-20ms/Window TBD와 충돌하며 vehicle.dbc/vehicle.ldf 최신본이 현재 첨부되지 않았으므로 본 시트는 Review 상태이며 Interface Freeze 불가. | [13 empty] | LIN ID 주의: 현재 0x11/0x12/0x14 값은 프로젝트 문서의 Frame ID/PID 표기를 그대로 참조한 값. Gateway 구현 전 최신 LDF에서 Protected PID를 별도 확인할 것. 상대 담당자 리뷰 필요.
ROUTE CONTROL |  |  | SOURCE INTERFACE | [5 empty] | ROUTING LOGIC / CACHE |  |  |  |  | DESTINATION INTERFACE / TIMING | [6 empty] | FAULT / TRACE / REVIEW
Route ID | Route Status | Requirement / Scenario | Source Network | Source Key (Message/Frame.Signal) | Source ID / PID | Source Node | Source Period (ms) | Source Interface Status | Trigger / Condition | Conversion Type | Conversion Rule / Function | Valid / Invalid / Stale Rule | Signal Cache Field | Destination Network | Destination Key (Message/Frame.Signal) | Destination ID / PID | Destination Node(s) | Destination Period / Tx Type | Delivery Timing | Schedule / Slot | Destination Fallback / Invalid | Fault / Timeout Link | Owner | Counterpart Reviewer | Jira / Issue | Test / Evidence | Source / Basis | Remark | Review Complete
C2L-001 | Review | MVP-1: Gear R → Reverse Lamp | CAN | VCU_Command.Gear | 0x100 | VCU | 10 | Needs Review | Gear == R(3) → ON; valid Gear != R → OFF | Enum→Bool | R(3) → 1; P/N/D(0/1/2) → 0; 그 외 raw(4~7) → 정상값으로 사용 금지 | 정의된 정상 Gear는 0=P,1=N,2=D,3=R만 허용. 4~5는 CAN_Matrix에서 OPEN, 6은 범위/문서 간 불일치, 7은 INVALID. raw 4~7 또는 VCU_Command timeout/alive 오류 시 source invalid 처리하고 ReverseLamp fallback은 별도 확정 필요 | vcu.gear (proposed) | LIN | Light_Command.ReverseLamp | Frame ID 0x12 / PID: LDF 확인 | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [TEAM/UNSYNCED] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | OPEN: source invalid/stale 시 ReverseLamp=0 또는 hold 여부를 Light/VCU/Gateway 리뷰로 확정 | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter | Gateway | VCU + Gateway + Light/LIN Common | TBD | CAN 0x100 Gear=R decode → LIN PID 0x12 ReverseLamp(bit4)=1 → Light output ON; non-R에서 0 확인 | HB 8.4~8.5; CAN_Matrix; 메시지 정의서 v0.3 LIN_Frame/Signal | MVP-1 경로는 타당. 단 Gear 4~7을 valid non-R로 취급하면 안 됨. LIN Matrix/LDF 동기화 후 Freeze. | ☐
C2L-002 | Review | Brake 입력 → Brake Lamp | CAN | VCU_Command.Brake | 0x100 | VCU | 10 | Needs Review | Brake == 1 → ON; Brake == 0 → OFF | Bool Copy | Brake → BrakeLamp | 정상 통신에서는 Brake 0/1을 그대로 사용. 단 CAN 정의의 Brake Invalid=1이 TRUE=1과 동일하여 signal-level invalid를 구분할 수 없음. VCU_Command message validity(timeout/alive)와 별개로 Interface 수정/정책 확정 필요 | vcu.brake (proposed) | LIN | Light_Command.BrakeLamp | Frame ID 0x12 / PID: LDF 확인 | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [TEAM/UNSYNCED] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | OPEN: VCU_Command invalid/stale 시 BrakeLamp 처리 정책 확정 필요 | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter | Gateway | VCU + Gateway + Light/LIN Common | TBD | CAN 0x100 Brake 0/1 decode → LIN PID 0x12 BrakeLamp(bit5) 0/1 → Light output 확인 | 기능 정의서 Light ECU 'Brake Lamp 제어: VCU Brake 연계'; CAN_Matrix; 메시지 정의서 v0.3 | 정상 경로 자체는 기능 정의서와 일치. Brake Invalid=1 ↔ TRUE=1 충돌 때문에 Interface Freeze 전 해결 필요. | ☐
C2L-003 | Blocked | Head Lamp command 전달 | CAN | TBD - CAN HeadLamp command signal 없음 | TBD | TBD |  | OPEN | CAN source signal 정의 후 결정 | Bool Copy | TBD CAN HeadLamp → HeadLamp | Source interface 미정 | TBD | LIN | Light_Command.HeadLamp | Frame ID 0x12 / PID: LDF 확인 | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [TEAM/UNSYNCED] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | Source interface 확정 후 정의 | TBD | Gateway / CAN Interface | VCU(or source ECU) + Gateway + Light/LIN Common | 필수: CAN Interface 추가 Issue | Source CAN signal/DBC 확정 전 test 불가 | 메시지 정의서 v0.3 Light_Command.HeadLamp; 현재 CAN_Matrix에 source 없음 | Destination LIN signal은 정의되어 있으나 CAN source가 없음. CAN→LIN Route로 구현하려면 source interface 신규 정의 또는 기능 범위 재결정 필요. 상대 담당자 리뷰 필요. | ☐
C2L-004 | Blocked | Turn Lamp command 전달 | CAN | TBD - CAN TurnLamp command signal 없음 | TBD | TBD |  | OPEN | CAN source signal 정의 후 결정 | Enum Mapping | TBD CAN turn state → OFF/LEFT/RIGHT | Source interface 미정 | TBD | LIN | Light_Command.TurnLamp | Frame ID 0x12 / PID: LDF 확인 | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [TEAM/UNSYNCED] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | Source interface 확정 후 정의 | TBD | Gateway / CAN Interface | VCU(or source ECU) + Gateway + Light/LIN Common | 필수: CAN Interface 추가 Issue | Source CAN signal/DBC 확정 전 test 불가 | 메시지 정의서 v0.3 Light_Command.TurnLamp; 현재 CAN_Matrix에 source 없음 | Destination LIN signal은 정의되어 있으나 CAN source가 없음. Turn source/state 정의 후 enum mapping 확정. 상대 담당자 리뷰 필요. | ☐
C2L-005 | Blocked | Hazard Lamp command 전달 | CAN | TBD - CAN Hazard command signal 없음 | TBD | TBD |  | OPEN | CAN source signal 정의 후 결정 | Bool Copy | TBD CAN Hazard → HazardLamp | Source interface 미정 | TBD | LIN | Light_Command.HazardLamp | Frame ID 0x12 / PID: LDF 확인 | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [TEAM/UNSYNCED] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | Source interface 확정 후 정의 | TBD | Gateway / CAN Interface | VCU(or source ECU) + Gateway + Light/LIN Common | 필수: CAN Interface 추가 Issue | Source CAN signal/DBC 확정 전 test 불가 | 메시지 정의서 v0.3 Light_Command.HazardLamp; 현재 CAN_Matrix에 source 없음 | Destination LIN signal은 정의되어 있으나 CAN source가 없음. Hazard 우선순위와 source 정의가 모두 필요. 상대 담당자 리뷰 필요. | ☐
C2L-006 | Blocked | Door Lock/Unlock request → Door Command | CAN | TBD - CAN Door Lock/Unlock request signal 없음 | TBD | VCU 또는 별도 command source TBD |  | OPEN | LOCK / UNLOCK request 수신 시 | Enum Mapping | LOCK→1, UNLOCK→2, no request→0 | Source interface 미정 | TBD | LIN | Door_Command.LockCommand | Frame ID 0x11 / PID: LDF 확인 | Door ECU | 100 ms / Scheduled | LIN Schedule Slot | [TEAM/UNSYNCED] BODY_10ms: 60 ms / entry 7 | NO_ACTION(0) 후보이나 source 정책 확정 전 Freeze 금지 | Door offline policy는 LIN→CAN/Health 측; source command timeout은 TBD | Gateway / CAN Interface | VCU(or source ECU) + Gateway + Door/LIN Common | 필수: CAN Interface 추가 Issue | Source CAN request → LIN PID 0x11 LockCommand → Door actuator/status E2E | Capella Door Lock/Unlock Request 흐름; 메시지 정의서 v0.3 Door_Command; 현재 CAN_Matrix에 source 없음 | Door 제어 기능은 In-Scope이나 현재 CAN_Matrix에 Lock/Unlock source signal이 없음. Source ECU/Message/Signal을 먼저 정의해야 함. 상대 담당자 리뷰 필요. | ☐
C2L-007 | Blocked | Window UP/DOWN command 전달 | CAN | TBD - CAN Window command signal 없음 | TBD | VCU/PC/별도 command source TBD |  | OPEN | STOP / UP / DOWN request 수신 시 | Enum Mapping | STOP→0, UP→1, DOWN→2 | Source interface 미정 | TBD | LIN | Window_Command.WindowCommand | Frame ID 0x14 / PID: LDF 확인 | Window ECU | 100 ms / Scheduled | LIN Schedule Slot | [TEAM/UNSYNCED] BODY_10ms: 10 ms / entry 2 | STOP(0) 후보이나 command timeout/local safety 정책과 함께 리뷰 필요 | WINDOW_ECU_OFFLINE / Window local command-timeout policy 연계 | Gateway / CAN Interface | Command source + Gateway + Window/LIN | 필수: CAN Interface 추가 Issue | Source CAN request → LIN PID 0x14 WindowCommand → Window ECU state/limit/status E2E | ARCH SYS_REQ_042-045/057; 메시지 정의서 v0.3 Window_Command; 현재 CAN_Matrix에 source 없음 | Window는 In-Scope이나 CAN source command가 정의되지 않음. 현재 LIN Team Encoding도 LIN_Matrix/LDF 미동기화 상태. 상대 담당자 리뷰 필요. | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
Note on A6: Route ID 권장: RT-C2L-### 또는 RT-L2C-###
Note on B6: Draft → Review → Frozen. Blocked는 Interface 미결정 등으로 진행 불가한 경우.
Note on E6: 예: VCU_Command.Gear / Door_Status.DoorOpen
Note on J6: 예: Gear == R, valid source only, value changed 등. 근거 없는 조건 추가 금지.
Note on K6: Copy / Bool Copy / Enum→Bool / Enum Mapping / Scale / Range Check / Bitmask / Fault Map / Custom Function
Note on M6: Invalid, stale, timeout 시 해당 route 입력을 어떻게 취급할지. 미확정이면 TBD/OPEN으로 유지.
Note on N6: Signal Cache 구조 설계에서 실제 필드명을 확정. Routing 설계 초안에서는 TBD 가능.
Note on T6: LIN 출력이면 Schedule Slot 연계, CAN 출력이면 Cyclic/Event 정책 연계.
Note on W6: VCU_TIMEOUT, DOOR_ECU_OFFLINE, ALIVE_ERROR 등 관련 Fault/Health 정책 링크.
Note on Y6: CAN/LIN Interface 경계가 걸린 변경은 상대 담당자 리뷰 필요.
Note on AD6: 체크는 리뷰 완료를 의미하며 Merge만으로 Done 처리하지 않음.

## LIN_to_CAN
Gateway Routing Table ¦ LIN → CAN
One row = one source signal → one destination signal route. DBC/LDF/Matrix 정의를 재설계하는 시트가 아니라, 확정된 Interface를 연결하는 Gateway 규칙을 관리합니다.
Baseline: current uploaded CAN_Matrix.xlsx / LIN_Matrix.xlsx snapshot. 실제 최신 vehicle.dbc / vehicle.ldf와 충돌 시 최신 실제 산출물 우선. | [13 empty] | 중요: CAN/LIN Interface 변경이 필요한 경우 Jira → Matrix/DBC/LDF → 상대 담당자 리뷰 필요 → Routing 반영 순서로 처리.
ROUTE CONTROL |  |  | SOURCE INTERFACE | [5 empty] | ROUTING LOGIC / CACHE |  |  |  |  | DESTINATION INTERFACE / TIMING | [6 empty] | FAULT / TRACE / REVIEW
Route ID | Route Status | Requirement / Scenario | Source Network | Source Key (Message/Frame.Signal) | Source ID / PID | Source Node | Source Period (ms) | Source Interface Status | Trigger / Condition | Conversion Type | Conversion Rule / Function | Valid / Invalid / Stale Rule | Signal Cache Field | Destination Network | Destination Key (Message/Frame.Signal) | Destination ID / PID | Destination Node(s) | Destination Period / Tx Type | Delivery Timing | Schedule / Slot | Destination Fallback / Invalid | Fault / Timeout Link | Owner | Counterpart Reviewer | Jira / Issue | Test / Evidence | Source / Basis | Remark | Review Complete
EX-L2C-001 | EXAMPLE | MVP-2: DoorOpen → Cluster/PC | LIN | Door_Status.DoorOpen | 0x10 | Door ECU | 100 | HANDBOOK FIXED | Valid Door_Status | Bool Copy | DoorOpen → Body_Status.DoorOpen | Door offline/invalid 정책 연계 | TBD (Signal Cache 설계) | CAN | Body_Status.DoorOpen | 0x200 | CLUSTER, PC_TOOL | 100 ms cyclic (uploaded Matrix) | CAN Cyclic | N/A | TBD / Review | DOOR_ECU_OFFLINE policy 연계 | Gateway | Gateway + Door/LIN + Cluster/PC | TBD | LIN response + CAN decode + Cluster/PC 표시 | HB 8.4~8.5 / current Matrix | 예시 행. 최신 DBC/LDF와 대조 후 실제 Route ID로 작성. | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
Note on A6: Route ID 권장: RT-C2L-### 또는 RT-L2C-###
Note on B6: Draft → Review → Frozen. Blocked는 Interface 미결정 등으로 진행 불가한 경우.
Note on E6: 예: VCU_Command.Gear / Door_Status.DoorOpen
Note on J6: 예: Gear == R, valid source only, value changed 등. 근거 없는 조건 추가 금지.
Note on K6: Copy / Bool Copy / Enum→Bool / Enum Mapping / Scale / Range Check / Bitmask / Fault Map / Custom Function
Note on M6: Invalid, stale, timeout 시 해당 route 입력을 어떻게 취급할지. 미확정이면 TBD/OPEN으로 유지.
Note on N6: Signal Cache 구조 설계에서 실제 필드명을 확정. Routing 설계 초안에서는 TBD 가능.
Note on T6: LIN 출력이면 Schedule Slot 연계, CAN 출력이면 Cyclic/Event 정책 연계.
Note on W6: VCU_TIMEOUT, DOOR_ECU_OFFLINE, ALIVE_ERROR 등 관련 Fault/Health 정책 링크.
Note on Y6: CAN/LIN Interface 경계가 걸린 변경은 상대 담당자 리뷰 필요.
Note on AD6: 체크는 리뷰 완료를 의미하며 Merge만으로 Done 처리하지 않음.

## Interface_Ref
Interface Reference Snapshot
현재 업로드된 CAN_Matrix.xlsx / LIN_Matrix.xlsx에서 Gateway 관련 Interface를 추출한 참고 시트. 실제 최신 DBC/LDF와 불일치 시 최신 산출물을 우선합니다.
A. CAN Gateway-related Signals (imported reference)
Key | Message | CAN ID | Signal | Sender | Receiver | Period (ms) | Factor | Offset | Min | Max | Unit | Invalid | Definition Status | Review Status
VCU_Command.TorqueRequest | VCU_Command | ​0x100 | TorqueRequest | VCU | MOTOR, GATEWAY, CLUSTER | 10 | 0.1 | 0 | 0 | 4000 | Nm | ​0xFFFF | Confirmed | Review
VCU_Command.Gear | VCU_Command | ​0x100 | Gear | VCU | MOTOR, GATEWAY, CLUSTER | 10 | 1 | 0 | 0 | 5 | enum | 7 | Confirmed | Review
VCU_Command.Brake | VCU_Command | ​0x100 | Brake | VCU | MOTOR, GATEWAY, CLUSTER | 10 | 1 | 0 | 0 | 1 | bool | 1 | Confirmed | Review
VCU_Command.AliveCounter | VCU_Command | ​0x100 | AliveCounter | VCU | MOTOR, GATEWAY, CLUSTER | 10 | 1 | 0 | 0 | 15 | count | ​0xF | Confirmed | Review
Motor_Status.RPM | Motor_Status | ​0x110 | RPM | MOTOR | VCU, GATEWAY, CLUSTER | 10 | 1 | 0 | 0 | 12000 | rpm | ​0xFFFF | Confirmed | Review
Motor_Status.TorqueApplied | Motor_Status | ​0x110 | TorqueApplied | MOTOR | VCU, GATEWAY, CLUSTER | 10 | [6 empty] | OPEN | OPEN
Motor_Status.MotorState | Motor_Status | ​0x110 | MotorState | MOTOR | VCU, GATEWAY, CLUSTER | 10 | [6 empty] | OPEN | OPEN
Motor_Status.AliveCounter | Motor_Status | ​0x110 | AliveCounter | MOTOR | VCU, GATEWAY, CLUSTER | 10 | [6 empty] | OPEN | OPEN
Vehicle_Status.Speed | Vehicle_Status | ​0x120 | Speed | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Vehicle_Status.RPM | Vehicle_Status | ​0x120 | RPM | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Vehicle_Status.Gear | Vehicle_Status | ​0x120 | Gear | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Vehicle_Status.Brake | Vehicle_Status | ​0x120 | Brake | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Vehicle_Status.NetworkState | Vehicle_Status | ​0x120 | NetworkState | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Body_Status.ReverseLamp | Body_Status | ​0x200 | ReverseLamp | GATEWAY | CLUSTER, PC_TOOL | 100 | 1 | 0 | 0 | 1 | bool | 1 | Confirmed | Review
Body_Status.DoorOpen | Body_Status | ​0x200 | DoorOpen | GATEWAY | CLUSTER, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Body_Status.LightStatus | Body_Status | ​0x200 | LightStatus | GATEWAY | CLUSTER, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Body_Status.WindowStatus | Body_Status | ​0x200 | WindowStatus | GATEWAY | CLUSTER, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Gateway_Status.GatewayAlive | Gateway_Status | ​0x300 | GatewayAlive | GATEWAY | ALL CAN NODES, PC_TOOL | 100 | 1 | 0 | 0 | 15 | count | ​0xF | Confirmed | Review
Gateway_Status.GatewayHealth | Gateway_Status | ​0x300 | GatewayHealth | GATEWAY | ALL CAN NODES, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Gateway_Status.QueueUsage | Gateway_Status | ​0x300 | QueueUsage | GATEWAY | ALL CAN NODES, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Gateway_Status.SystemState | Gateway_Status | ​0x300 | SystemState | GATEWAY | ALL CAN NODES, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Fault_Status.FaultCode | Fault_Status | ​0x310 | FaultCode | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultSource | Fault_Status | ​0x310 | FaultSource | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultSeverity | Fault_Status | ​0x310 | FaultSeverity | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultState | Fault_Status | ​0x310 | FaultState | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultRecovery | Fault_Status | ​0x310 | FaultRecovery | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultMultiFault | Fault_Status | ​0x310 | FaultMultiFault | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
B. LIN Gateway-related Signals (imported reference)
Key | Frame | PID | Signal | Publisher | Subscriber | Period (ms) | Factor | Offset | Min | Max | Unit | Invalid | Status | Review Needed
Door_Status.DoorOpen | Door_Status | 0x10 | DoorOpen | Door ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Door_Status.DoorLocked | Door_Status | 0x10 | DoorLocked | Door ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Door_Status.DoorAlive | Door_Status | 0x10 | DoorAlive | Door ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Door_Command.LockCommand | Door_Command | 0x11 | LockCommand | Gateway ECU | Door ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Door_Command.RequestState | Door_Command | 0x11 | RequestState | Gateway ECU | Door ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.HeadLamp | Light_Command | 0x12 | HeadLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.TurnLamp | Light_Command | 0x12 | TurnLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.HazardLamp | Light_Command | 0x12 | HazardLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.ReverseLamp | Light_Command | 0x12 | ReverseLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.BrakeLamp | Light_Command | 0x12 | BrakeLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Status.LampState | Light_Status | 0x13 | LampState | Light ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Status.LightAlive | Light_Status | 0x13 | LightAlive | Light ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Status.DiagnosticState | Light_Status | 0x13 | DiagnosticState | Light ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Window_Command.TBD / OPEN | Window_Command | TBD / OPEN | TBD / OPEN | Gateway ECU | Window ECU | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | 상대 담당자 리뷰 필요
Window_Status.TBD / OPEN | Window_Status | TBD / OPEN | TBD / OPEN | Window ECU | Gateway ECU | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | 상대 담당자 리뷰 필요
C. LIN Schedule Snapshot (imported reference)
Schedule ID | Cycle / Set | Slot Time (ms) | Entry | Frame Name | PID | Direction / Header | Master Action | Expected Response / Effect | Period Reference | Status | Review Needed | Owner / Reviewer | Source / Basis | Notes
LS-001 | BASE-20ms | 0 | 1 | Door_Status | 0x10 | Gateway Header -> Door; Door Response -> Gateway | Poll Door_Status | DoorOpen, DoorLocked, DoorAlive response | 100 ms frame / 20 ms base slot | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common + Door | Handbook v1.0 §6.2–6.3 (p.18–19) | First slot in the fixed baseline schedule.
LS-002 | BASE-20ms | 20 | 2 | Light_Command | 0x12 | Gateway -> Light | Publish Light_Command | Light ECU accepts Head/Turn/Hazard/Reverse/Brake command | 50 ms frame / 20 ms base slot | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common + Light | Handbook v1.0 §6.2–6.3 (p.18–19) | Second slot in the fixed baseline schedule.
LS-003 | BASE-20ms | 40 | 3 | Light_Status | 0x13 | Gateway Header -> Light; Light Response -> Gateway | Poll Light_Status | LampState, LightAlive, DiagnosticState response | 100 ms frame / 20 ms base slot | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common + Light | Handbook v1.0 §6.2–6.3 (p.18–19) | Third slot in the fixed baseline schedule.
LS-004 | BASE-20ms | 60 | 4 | Door_Command | 0x11 | Gateway -> Door | Publish Door_Command | Door ECU accepts LockCommand / RequestState | 100 ms frame / 20 ms base slot | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common + Door | Handbook v1.0 §6.2–6.3 (p.18–19) | Fourth slot in the fixed baseline schedule.
LS-005 | BASE-20ms | 100 | repeat | Schedule 0 repeat | n.a. | Gateway Master timing | Repeat from t=0 | 100 ms repeat boundary; 20 ms base schedule continues | 100 ms repeat | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common | Handbook v1.0 §6.2–6.3 (p.18–19) | Repeat marker; not a LIN frame PID.
LS-006 | WINDOW-EXT | TBD / OPEN | TBD / OPEN | Window_Command | TBD / OPEN | Gateway -> Window | Window command slot TBD / OPEN | Window ECU accepts UP/DOWN command; detailed response/data TBD / OPEN | TBD / OPEN | TBD / OPEN | 상대 담당자 리뷰 필요 | Gateway + Window + Test | System Architecture Spec v1.0 §8.2–8.3 (p.16); §12 OPN-07 (p.21) | Do not assign a fixed slot before Window interface review.
LS-007 | WINDOW-EXT | TBD / OPEN | TBD / OPEN | Window_Status | TBD / OPEN | Window -> Gateway | Window status response slot TBD / OPEN | Limit/status response; detailed response/data TBD / OPEN | TBD / OPEN | TBD / OPEN | 상대 담당자 리뷰 필요 | Gateway + Window + Test | System Architecture Spec v1.0 §8.2–8.3 (p.16); §12 OPN-07/08 (p.21) | Window offline threshold and recovery policy are also TBD / OPEN.

## Change_Log
Routing Change Log
Routing 규칙 변경 및 Interface 영향 추적. CAN/LIN Interface 변경은 상대 담당자 리뷰 필요.
Routing / Interface Change Control
Change ID | Date | Jira / Issue | Route ID | Target | Old Definition | New Definition | Reason / Decision | Affected ECU / Team | Author | Counterpart Reviewer | Status | Evidence / Link | Remark
RT-INIT-001 | 2026-10-01 | TBD | C2L-001~007 | CAN→LIN Routing initial population | Template example only | 2 routable paths + 5 interface gaps identified | Populate routing based on current CAN Matrix and latest message definition Team Encoding | VCU / Gateway / Light / Door / Window / CAN / LIN | Gateway | 상대 담당자 리뷰 필요 | Review | CAN_Matrix.xlsx; 메시지 정의서_v0.3_점검완료.xlsx | vehicle.dbc / vehicle.ldf 최신본과 대조 후 Freeze. Merge != Done.
RT-REV-002 | 2026-10-01 | TBD | C2L-001~007 | CAN→LIN Routing technical review | v0.2 | v0.3 Reviewed | Gear reserved handling correction; Brake invalid conflict flagged; LIN baseline/PID ambiguity noted; blocked source gaps retained | VCU / Gateway / CAN / LIN / Door / Light / Window | Gateway | 상대 담당자 리뷰 필요 | Review | CAN_Matrix.xlsx; LIN_Matrix.xlsx; 메시지 정의서_v0.3; 기능 정의서; Handbook/ARCH | Freeze blocker는 Review_Summary 참조.