## README
Gateway Routing Table ¦ 작성 가이드
FreeRTOS CAN-LIN Gateway 프로젝트의 CAN↔LIN Signal Routing 규칙을 설계·리뷰·Freeze하기 위한 협업용 Excel 양식
1. Workbook Baseline
| Project | FreeRTOS CAN-LIN Gateway 7인 팀 프로젝트 | Gateway 설계 단계
| Purpose | CAN→LIN / LIN→CAN source → condition/conversion → destination Routing 규칙 정의 | Routing Table은 DBC/LDF 자체를 재정의하지 않음
| Reference | CAN-LIN Gateway Handbook v1.0 §8.3~8.5 / Project 시퀀스 Phase 4 | 현재 업로드된 CAN_Matrix.xlsx / LIN_Matrix.xlsx 참조
| Priority rule | 실제 최신 vehicle.dbc / vehicle.ldf / Matrix가 Handbook 예시보다 우선 | 충돌 시 먼저 충돌 사실 확인 후 수정
| Change rule | Interface 변경: Jira → Matrix/DBC/LDF → 상대 담당자 리뷰 필요 → Routing → FW/Tool/Test | Merge ≠ Done
v0.4 기준안 | Review v0.3 | CAN→LIN 7개 항목 검토 완료 | C2L-001/002는 Review, C2L-003~007은 CAN source 부재로 Blocked. Freeze blocker는 Review_Summary 참조.
CAN→LIN 7개 Route의 설계 decision은 완료. 공식 Interface Freeze는 Required_Interface_Changes 반영 + 상대 담당자 리뷰 + 최신 DBC/LDF 검증 후.
| 1 | Gateway 관련 Signal 추출 | DBC/LDF/Matrix에서 Gateway가 실제로 소비·생성하는 Signal만 식별
| 2 | CAN → LIN 작성 | CAN Source → 조건/변환 → LIN Destination 매핑
| 3 | LIN → CAN 작성 | LIN Source → 조건/변환 → CAN Destination 매핑
| 4 | Invalid/Timing 연계 | valid/stale/timeout 및 LIN Schedule/CAN Tx 정책 연결
| 5 | Signal Cache 필드 연결 | 최신 값, valid, timestamp/alive 상태를 보관할 Cache field 연결
| 6 | 상대 담당자 리뷰 | Interface 경계의 의미·방향·주기·conversion 합의
| 7 | Freeze 후 코드화 | routing_table.c/.h, RoutingTask, test case로 반영
3. 핵심 작성 규칙
| • | 한 행은 1개의 Source Signal → 1개의 Destination Signal route를 의미합니다.
| • | 동일 Source가 여러 Destination으로 가면 route를 여러 행으로 분리합니다.
| • | Routing Table에서 새로운 CAN/LIN Signal을 임의로 만들지 않습니다. 새 Signal이 필요하면 Interface Change 절차를 먼저 수행합니다.
| • | 조건/변환은 코드처럼 명확하게 적되, 근거 없는 임계값이나 timing 숫자를 새로 만들지 않습니다.
| • | LIN Destination은 최신 LDF Schedule과 연결하고, CAN Destination은 Cyclic/Event 정책과 연결합니다.
| • | OPEN/TBD Interface는 Routing도 OPEN/TBD로 남기고 확정처럼 작성하지 않습니다.
| • | CAN/LIN Interface 변경 관련 행은 반드시 상대 담당자 리뷰 필요입니다.
4. Status / Color Legend
| Blue text | 사용자가 직접 작성/수정하는 Routing 입력
| Green text | CAN/LIN Matrix에서 가져온 참고 데이터
| Gray | 고정값 / 예시 / 방향 상수
| Orange | 리뷰 필요 / Interface Change 주의
| Light red | Blocked / 오류 / 충돌
5. Route ID / Status 권장
| RT-C2L-### | CAN → LIN route
| RT-L2C-### | LIN → CAN route
| Draft | 작성 중
| Review | 상대 담당자/시스템 담당 리뷰 중
| Frozen | Interface Freeze 승인
| Blocked | Interface 미정/충돌로 보류
| EXAMPLE | 양식 설명용 예시 행

## Decision_Baseline
CAN→LIN Routing Decision Baseline ¦ v0.4
이 시트는 Gateway Routing 설계를 진행하기 위한 팀 기준안입니다. 아래 내용은 설계상 우선 확정하되, CAN/LIN Interface 변경분은 프로젝트 규칙상 상대 담당자 리뷰 + Matrix/DBC/LDF 동기화 전에는 공식 Interface Freeze로 취급하지 않습니다.
Decision ID | Decision Area | v0.4 Decision | Reason / Basis | Affected Route | Required Interface Change | Review Owner | Design Decision | Official Freeze
DEC-01 | CAN body-command source | Body 제어용 CAN Source는 VCU_Command의 기존 Reserved Byte3(bit 24~31)에 추가한다. | VCU는 Driver/User 입력의 CAN Command 생성 주체이고 VCU_Command는 Byte3~7이 Reserved 상태. 신규 CAN Message ID를 만들지 않고 기존 주기/수신 경로를 재사용. | C2L-003~007 | CAN_Matrix + vehicle.dbc에 신규 Signal 5개 추가 | VCU + Gateway + CAN + Door/Light/Window | DECIDED | PENDING REVIEW
DEC-02 | VCU_Command Byte3 bit allocation | bit24 HeadLampRequest(1), bit25~26 TurnLampRequest(2), bit27 HazardLampRequest(1), bit28~29 DoorLockRequest(2), bit30~31 WindowCommand(2). | 현재 Byte3 전체 8 bit가 Reserved이며 5개 command가 정확히 8 bit에 수용됨. LIN destination enum과 직접 매핑 가능. | C2L-003~007 | CAN_Matrix/DBC bit layout 변경 | VCU + Gateway + CAN | DECIDED | PENDING REVIEW
DEC-03 | 1-bit Boolean invalid policy | Brake/HeadLamp/Hazard 등 1-bit bool은 signal-level Invalid code를 사용하지 않고, VCU_Command message validity(age/alive)로 invalid/stale를 판단한다. | 1-bit bool은 0/1이 모두 정상 의미이므로 별도 Invalid raw 값을 동시에 표현할 수 없음. 현재 Brake Invalid=1은 TRUE=1과 충돌. | C2L-002/003/005 | VCU_Command.Brake Invalid=1 → N/A. 신규 1-bit command도 Invalid=N/A | VCU + Gateway + CAN | DECIDED | PENDING REVIEW
DEC-04 | Safe fallback | VCU_Command invalid/stale 또는 개별 enum invalid 시 Lamp commands=OFF(0), DoorLock=NO_ACTION(0), Window=STOP(0)으로 전송한다. | 잘못된 명령의 지속 전달을 막고, Door/Window는 동작 정지/무동작 상태로 복귀시키는 단순·재현 가능한 기본 정책. | C2L-001~007 | Routing/FW/Test 정책 반영 | Gateway + affected ECU | DECIDED | PENDING REVIEW
DEC-05 | LIN schedule baseline | Routing 설계 기준은 BODY_10ms: 10 ms slot / 100 ms supercycle. Window_Command 10 ms, Light_Command 20/70 ms, Door_Command 60 ms slot을 사용한다. | 메시지 정의서 v0.3 Team Encoding의 최신 프로젝트안. 기존 LIN_Matrix BASE-20ms와 충돌하므로 산출물 동기화 필요. | All C2L | LIN_Matrix/LIN_Schedule/LDF를 BODY_10ms로 업데이트 | Gateway + LIN Common + Door/Light/Window | DECIDED | PENDING REVIEW
DEC-06 | LIN Frame ID / PID notation | Routing Table에는 0x11/0x12/0x14를 Frame ID로 기록하고, 실제 Protected PID는 최신 LDF에서 산출/검증한다. | Frame ID와 Protected PID 혼용 방지. Gateway 저수준 LIN Header 구현 시 LDF가 최종 기준. | All LIN destinations | LDF 생성/검증 후 PID evidence 기록 | Gateway + LIN Common | DECIDED | PENDING LDF
DEC-07 | Door RequestState handling | CAN→LIN Routing에서는 LockCommand만 매핑하고 RequestState는 정상 동작에서 NO_REQUEST(0) 유지. Door_Status는 Schedule polling으로 수집한다. | 현재 Door_Status가 주기 polling되므로 별도 CAN request source 없이도 상태 수집 가능. 불필요한 command source 확대 방지. | C2L-006 | Gateway Door_Command encoder 정책 반영 | Gateway + Door/LIN | DECIDED | PENDING REVIEW
DEC-08 | Hazard vs Turn priority | Gateway는 TurnLamp와 HazardLamp를 각각 그대로 전달하고, 실제 Lamp 출력 우선순위는 Light ECU에서 Hazard=1 우선으로 처리한다. | Light ECU가 최종 Lamp output owner이며 기능 정의서에 Hazard 우선순위 정책 문서화 필요가 명시됨. | C2L-004/005 | Light ECU application/test 정책 반영 | Light + Gateway | DECIDED | PENDING REVIEW

## Required_Interface_Changes
Required Interface Changes before Official Freeze
v0.4 Routing 기준안을 실제 Interface 산출물에 반영해야 하는 변경 목록. 모든 CAN/LIN Interface 변경은 상대 담당자 리뷰 필요.
Change ID | Artifact | Message/Frame | Signal | Start Bit | Length | Encoding | Initial | Invalid | Change | Reviewer | Status
IFC-01 | CAN_Matrix + DBC | VCU_Command | Brake | 19 | 1 | bool 0/1 | 0 | N/A | Invalid=1 제거. message validity(age/alive)로 invalid/stale 판단 | VCU + Gateway + CAN | Review
IFC-02 | CAN_Matrix + DBC | VCU_Command | HeadLampRequest | 24 | 1 | bool 0=OFF,1=ON | 0 | N/A | Reserved bit → 신규 body command | VCU + Gateway + Light | Review
IFC-03 | CAN_Matrix + DBC | VCU_Command | TurnLampRequest | 25 | 2 | 0=OFF,1=LEFT,2=RIGHT,3=INVALID | 0 | 3 | Reserved bits → 신규 body command | VCU + Gateway + Light | Review
IFC-04 | CAN_Matrix + DBC | VCU_Command | HazardLampRequest | 27 | 1 | bool 0=OFF,1=ON | 0 | N/A | Reserved bit → 신규 body command | VCU + Gateway + Light | Review
IFC-05 | CAN_Matrix + DBC | VCU_Command | DoorLockRequest | 28 | 2 | 0=NO_ACTION,1=LOCK,2=UNLOCK,3=INVALID | 0 | 3 | Reserved bits → 신규 body command | VCU + Gateway + Door | Review
IFC-06 | CAN_Matrix + DBC | VCU_Command | WindowCommand | 30 | 2 | 0=STOP,1=UP,2=DOWN,3=INVALID | 0 | 3 | Reserved bits → 신규 body command | VCU + Gateway + Window | Review
IFC-07 | LIN_Matrix/Schedule/LDF | BODY_10ms | Schedule |  |  | 10 ms slot / 100 ms supercycle |  |  | BASE-20ms 구형안 → BODY_10ms 최신 기준안 동기화 | Gateway + LIN Common + Door/Light/Window | Review
IFC-08 | LDF | Door/Light/Window frames | Protected PID |  |  | derive from Frame ID |  |  | Frame ID와 Protected PID 분리 검증 | Gateway + LIN Common | Pending LDF

## Review_Summary
CAN→LIN Routing Review Summary ¦ v0.4 Decision Baseline
설계 공백에 대해 v0.4 기준안을 결정함. 단 CAN/LIN Interface 변경분은 상대 담당자 리뷰와 Matrix/DBC/LDF 동기화 전 공식 Freeze가 아님.
ID | Severity | Affected Route | Finding | Why it matters | Required Action | Freeze Blocker | Review | v0.4 Decision / Resolution
REV-01 | HIGH | All C2L | LIN baseline 불일치: LIN_Matrix.xlsx는 BASE-20ms/Window TBD, 메시지 정의서_v0.3은 BODY_10ms/Window 0x14 등 Team Encoding 사용 | Routing slot/period가 어느 기준인지 확정되지 않으면 구현·PulseView 검증 기준이 달라짐 | LIN_Matrix/LIN_Schedule/LDF를 BODY_10ms 기준으로 동기화 후 counterpart review | YES | 상대 담당자 리뷰 필요 | BODY_10ms를 Routing 기준안으로 채택. LIN_Matrix/LDF 동기화가 남음.
REV-02 | HIGH | C2L-002 | VCU_Command.Brake의 Invalid=1이 정상 TRUE=1과 동일 | 1-bit raw 값만으로 정상 Brake ON과 signal invalid를 구분할 수 없음 | CAN_Matrix/DBC에서 Brake Invalid=1을 N/A로 변경하고 message-level validity test 추가 | YES | VCU + Gateway + CAN 담당 | Brake signal-level Invalid 제거(N/A), VCU_Command message validity(age/alive) 사용.
REV-03 | MEDIUM | C2L-001 | Gear 4~7 처리 불명확/문서 간 차이. 정상 정의는 P/N/D/R(0~3)뿐 | 기존 v0.2의 “기타 valid gear→0”은 OPEN/RESERVED 값을 정상값으로 오인 가능 | CAN Matrix/DBC에서 Gear enum/invalid 범위 정리 후 test에 raw 4~7 case 포함 | NO* | VCU + Gateway (*Freeze 전 source 정의는 정리 필요) | Gear 0~3만 정상. raw 4~7은 invalid/reserved, ReverseLamp fallback=OFF.
REV-04 | HIGH | C2L-003~007 | Head/Turn/Hazard/Door Lock/Window 명령의 CAN source Message/Signal이 현재 CAN_Matrix에 없음 | Destination LIN command는 있어도 CAN→LIN 입력이 없으므로 Routing 구현 불가 | VCU_Command Byte3 신규 Signal 5개를 Matrix/DBC에 반영하고 VCU/GW/각 LIN ECU 리뷰 | YES | 상대 담당자 리뷰 필요 | VCU_Command Byte3(bit24~31)에 Head/Turn/Hazard/Door/Window command를 배치하는 기준안 결정.
REV-05 | MEDIUM | All LIN destination | Frame ID와 Protected PID 표기가 혼재 | Gateway 저수준 LIN 구현에서는 실제 PID 확인이 필요하며 0x1x 값을 그대로 PID로 오해할 위험 | LDF 생성 후 Protected PID capture로 검증 | YES (implementation) | Gateway + LIN Common | Routing 표에는 Frame ID만 기록. Protected PID는 LDF에서 산출/검증.
REV-06 | HIGH | All | 현재 프로젝트 첨부 기준 vehicle.dbc / vehicle.ldf 최신본을 직접 대조하지 못함 | Matrix/메시지 정의서와 실제 DB 파일이 다르면 Routing bit/enum/slot이 틀릴 수 있음 | 최신 DBC/LDF를 첨부/생성하여 Matrix diff + cantools/LDF 검증 | YES | Gateway + CAN/LIN + PC/Test | 최신 vehicle.dbc/vehicle.ldf 대조는 여전히 필수. 이 항목만 문서/DB 부재로 미해결.

## _LISTS (hidden)
Route Status | Interface Status | Conversion Type | Delivery Timing | Review Complete
Draft | Confirmed | Copy | On Cache Update | ☐
Review | Team Decision | Bool Copy | LIN Schedule Slot | ☑
Frozen | OPEN | Enum→Bool | CAN Cyclic
Blocked | TBD / OPEN | Enum Mapping | CAN Event
EXAMPLE | Needs Review | Scale | Periodic Snapshot
|  | Range Check | On Change
|  | Bitmask | TBD / OPEN
Fault Map
Custom Function

## CAN_to_LIN
Gateway Routing Table ¦ CAN → LIN
One row = one source signal → one destination signal route. DBC/LDF/Matrix 정의를 재설계하는 시트가 아니라, 확정된 Interface를 연결하는 Gateway 규칙을 관리합니다.
v0.4 Decision Baseline: Body command CAN source는 VCU_Command Byte3에 배치하고, BODY_10ms Schedule을 Routing 기준으로 사용. 단 공식 Interface Freeze는 상대 담당자 리뷰 + CAN_Matrix/DBC + LIN_Matrix/LDF 동기화 후. | [13 empty] | LIN ID 주의: 현재 0x11/0x12/0x14 값은 프로젝트 문서의 Frame ID/PID 표기를 그대로 참조한 값. Gateway 구현 전 최신 LDF에서 Protected PID를 별도 확인할 것. 상대 담당자 리뷰 필요.
ROUTE CONTROL |  |  | SOURCE INTERFACE | [5 empty] | ROUTING LOGIC / CACHE |  |  |  |  | DESTINATION INTERFACE / TIMING | [6 empty] | FAULT / TRACE / REVIEW
Route ID | Route Status | Requirement / Scenario | Source Network | Source Key (Message/Frame.Signal) | Source ID / PID | Source Node | Source Period (ms) | Source Interface Status | Trigger / Condition | Conversion Type | Conversion Rule / Function | Valid / Invalid / Stale Rule | Signal Cache Field | Destination Network | Destination Key (Message/Frame.Signal) | Destination ID / PID | Destination Node(s) | Destination Period / Tx Type | Delivery Timing | Schedule / Slot | Destination Fallback / Invalid | Fault / Timeout Link | Owner | Counterpart Reviewer | Jira / Issue | Test / Evidence | Source / Basis | Remark | Review Complete
C2L-001 | Review | MVP-1: Gear R → Reverse Lamp | CAN | VCU_Command.Gear | 0x100 | VCU | 10 | Confirmed | Gear == R(3) → ReverseLamp ON; P/N/D(0/1/2) → OFF | Enum→Bool | R(3)→1; P/N/D(0/1/2)→0; raw 4~7은 invalid/reserved 처리 | 정상 Gear=0~3만 허용. raw 4~7 또는 VCU_Command age/alive invalid 시 route input invalid. | vcu.gear | LIN | Light_Command.ReverseLamp | Frame ID 0x12 / PID: LDF 확인 | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [DEC-05] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | OFF(0) | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter | Gateway | VCU + Gateway + Light/LIN Common | Interface review / DBC-LDF sync issue 필요 | CAN 0x100 Gear=3 → cache gear=R → Light_Command.ReverseLamp(bit4)=1; Gear=0/1/2 및 invalid/stale → 0 | HB 8.4~8.5 + CAN_Matrix + 메시지 정의서 v0.3 + DEC-04/05 | Routing logic 기준안 확정. 공식 Freeze는 최신 DBC/LDF 및 상대 담당자 리뷰 후. | ☐
C2L-002 | Review | Brake 입력 → Brake Lamp | CAN | VCU_Command.Brake | 0x100 | VCU | 10 | Team Decision | Brake == 1 → ON; Brake == 0 → OFF | Bool Copy | Brake raw bool 그대로 BrakeLamp에 copy | Brake 0/1은 모두 정상값. signal-level Invalid code 미사용. VCU_Command age/alive로 message validity 판단. | vcu.brake | LIN | Light_Command.BrakeLamp | Frame ID 0x12 / PID: LDF 확인 | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [DEC-05] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | OFF(0) | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter | Gateway | VCU + Gateway + Light/LIN Common | 필수: Brake Invalid 정책 CAN_Matrix/DBC 변경 Issue | Brake=0/1 각각 LIN BrakeLamp(bit5)=0/1 확인; VCU timeout/alive invalid 시 0 + Fault/Log 확인 | 기능 정의서 Light ECU Brake Lamp + CAN_Matrix + DEC-03/04/05 | Brake Invalid=1은 삭제(N/A)하는 방향으로 기준안 확정. 상대 담당자 리뷰 필요. | ☐
C2L-003 | Review | Head Lamp command 전달 | CAN | VCU_Command.HeadLampRequest | 0x100 | VCU | 10 | Team Decision | HeadLampRequest 1→ON, 0→OFF | Bool Copy | HeadLampRequest → HeadLamp | 0/1 정상. 별도 signal invalid 없음; VCU_Command age/alive로 validity 판단. | vcu.head_lamp_request | LIN | Light_Command.HeadLamp | Frame ID 0x12 / PID: LDF derived | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [DEC-05] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | OFF(0) | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter | VCU + Gateway | VCU + Gateway + Light/LIN Common | 필수: VCU_Command Byte3 Interface Change | VCU_Command bit24 0/1 → Light_Command.HeadLamp(bit0) 0/1 → Light output 확인 | DEC-01/02/03/04/05 + 메시지 정의서 v0.3 | CAN source를 VCU_Command bit24로 기준안 확정. CAN_Matrix/DBC 반영 후 공식 Freeze. | ☐
C2L-004 | Review | Turn Lamp command 전달 | CAN | VCU_Command.TurnLampRequest | 0x100 | VCU | 10 | Team Decision | 0=OFF, 1=LEFT, 2=RIGHT, 3=INVALID | Enum Mapping | CAN 0/1/2 → LIN TurnLamp 0/1/2; 3 → OFF fallback | 0~2 정상, 3 invalid. VCU_Command stale/invalid도 route invalid. | vcu.turn_lamp_request | LIN | Light_Command.TurnLamp | Frame ID 0x12 / PID: LDF derived | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [DEC-05] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | OFF(0) | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter | VCU + Gateway | VCU + Gateway + Light/LIN Common | 필수: VCU_Command Byte3 Interface Change | VCU_Command bits25~26 0/1/2/3 → Light_Command.TurnLamp(bits1~2) 기대값/invalid fallback 확인 | DEC-01/02/04/05/08 + 메시지 정의서 v0.3 | CAN source를 VCU_Command bits25~26으로 기준안 확정. Hazard 우선순위는 Light ECU에서 처리. | ☐
C2L-005 | Review | Hazard Lamp command 전달 | CAN | VCU_Command.HazardLampRequest | 0x100 | VCU | 10 | Team Decision | HazardLampRequest 1→ON, 0→OFF | Bool Copy | HazardLampRequest → HazardLamp | 0/1 정상. 별도 signal invalid 없음; VCU_Command age/alive로 validity 판단. | vcu.hazard_lamp_request | LIN | Light_Command.HazardLamp | Frame ID 0x12 / PID: LDF derived | Light ECU | 50 ms / Scheduled | LIN Schedule Slot | [DEC-05] BODY_10ms: 20 ms / entry 3, 70 ms / entry 8 | OFF(0) | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter | VCU + Gateway | VCU + Gateway + Light/LIN Common | 필수: VCU_Command Byte3 Interface Change | VCU_Command bit27 0/1 → Light_Command.HazardLamp(bit3) 0/1; Hazard=1 시 Light ECU 양측 Turn 출력 확인 | DEC-01/02/03/04/05/08 + 메시지 정의서 v0.3 | CAN source를 VCU_Command bit27로 기준안 확정. 실제 output 우선순위는 Light ECU. | ☐
C2L-006 | Review | Door Lock/Unlock request → Door Command | CAN | VCU_Command.DoorLockRequest | 0x100 | VCU | 10 | Team Decision | 0=NO_ACTION, 1=LOCK, 2=UNLOCK, 3=INVALID | Enum Mapping | CAN 0/1/2 → LIN LockCommand 0/1/2; 3 → NO_ACTION | 0~2 정상, 3 invalid. stale/invalid 시 NO_ACTION. | vcu.door_lock_request | LIN | Door_Command.LockCommand | Frame ID 0x11 / PID: LDF derived | Door ECU | 100 ms / Scheduled | LIN Schedule Slot | [DEC-05] BODY_10ms: 60 ms / entry 7 | NO_ACTION(0); RequestState=NO_REQUEST(0) | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter; Door offline은 LIN Health 경로 | VCU + Gateway | VCU + Gateway + Door/LIN Common | 필수: VCU_Command Byte3 Interface Change | VCU_Command bits28~29 0/1/2/3 → Door_Command.LockCommand(bits0~1) 0/1/2/0 확인; Door actuator/status E2E | DEC-01/02/04/05/07 + 메시지 정의서 v0.3 | CAN source를 VCU_Command bits28~29로 기준안 확정. RequestState는 정상 routing에서 0 유지. | ☐
C2L-007 | Review | Window UP/DOWN command 전달 | CAN | VCU_Command.WindowCommand | 0x100 | VCU | 10 | Team Decision | 0=STOP, 1=UP, 2=DOWN, 3=INVALID | Enum Mapping | CAN 0/1/2 → LIN WindowCommand 0/1/2; 3 → STOP | 0~2 정상, 3 invalid. stale/invalid 시 STOP. | vcu.window_command | LIN | Window_Command.WindowCommand | Frame ID 0x14 / PID: LDF derived | Window ECU | 100 ms / Scheduled | LIN Schedule Slot | [DEC-05] BODY_10ms: 10 ms / entry 2 | STOP(0) | VCU_TIMEOUT(age > 30 ms), VCU AliveCounter; Window local timeout/limit safety 별도 | VCU + Gateway | VCU + Gateway + Window/LIN | 필수: VCU_Command Byte3 Interface Change | VCU_Command bits30~31 0/1/2/3 → Window_Command bits0~1 0/1/2/0; limit switch/local STOP E2E 확인 | DEC-01/02/04/05 + ARCH SYS_REQ_042~045 + 메시지 정의서 v0.3 | CAN source를 VCU_Command bits30~31로 기준안 확정. Window local safety는 Window ECU가 수행. | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
|  |  | CAN | [10 empty] | LIN | [14 empty] | ☐
Note on A6: Route ID 권장: RT-C2L-### 또는 RT-L2C-###
Note on B6: Draft → Review → Frozen. Blocked는 Interface 미결정 등으로 진행 불가한 경우.
Note on E6: 예: VCU_Command.Gear / Door_Status.DoorOpen
Note on J6: 예: Gear == R, valid source only, value changed 등. 근거 없는 조건 추가 금지.
Note on K6: Copy / Bool Copy / Enum→Bool / Enum Mapping / Scale / Range Check / Bitmask / Fault Map / Custom Function
Note on M6: Invalid, stale, timeout 시 해당 route 입력을 어떻게 취급할지. 미확정이면 TBD/OPEN으로 유지.
Note on N6: Signal Cache 구조 설계에서 실제 필드명을 확정. Routing 설계 초안에서는 TBD 가능.
Note on T6: LIN 출력이면 Schedule Slot 연계, CAN 출력이면 Cyclic/Event 정책 연계.
Note on W6: VCU_TIMEOUT, DOOR_ECU_OFFLINE, ALIVE_ERROR 등 관련 Fault/Health 정책 링크.
Note on Y6: CAN/LIN Interface 경계가 걸린 변경은 상대 담당자 리뷰 필요.
Note on AD6: 체크는 리뷰 완료를 의미하며 Merge만으로 Done 처리하지 않음.

## LIN_to_CAN
Gateway Routing Table ¦ LIN → CAN
One row = one source signal → one destination signal route. DBC/LDF/Matrix 정의를 재설계하는 시트가 아니라, 확정된 Interface를 연결하는 Gateway 규칙을 관리합니다.
Baseline: current uploaded CAN_Matrix.xlsx / LIN_Matrix.xlsx snapshot. 실제 최신 vehicle.dbc / vehicle.ldf와 충돌 시 최신 실제 산출물 우선. | [13 empty] | 중요: CAN/LIN Interface 변경이 필요한 경우 Jira → Matrix/DBC/LDF → 상대 담당자 리뷰 필요 → Routing 반영 순서로 처리.
ROUTE CONTROL |  |  | SOURCE INTERFACE | [5 empty] | ROUTING LOGIC / CACHE |  |  |  |  | DESTINATION INTERFACE / TIMING | [6 empty] | FAULT / TRACE / REVIEW
Route ID | Route Status | Requirement / Scenario | Source Network | Source Key (Message/Frame.Signal) | Source ID / PID | Source Node | Source Period (ms) | Source Interface Status | Trigger / Condition | Conversion Type | Conversion Rule / Function | Valid / Invalid / Stale Rule | Signal Cache Field | Destination Network | Destination Key (Message/Frame.Signal) | Destination ID / PID | Destination Node(s) | Destination Period / Tx Type | Delivery Timing | Schedule / Slot | Destination Fallback / Invalid | Fault / Timeout Link | Owner | Counterpart Reviewer | Jira / Issue | Test / Evidence | Source / Basis | Remark | Review Complete
EX-L2C-001 | EXAMPLE | MVP-2: DoorOpen → Cluster/PC | LIN | Door_Status.DoorOpen | 0x10 | Door ECU | 100 | HANDBOOK FIXED | Valid Door_Status | Bool Copy | DoorOpen → Body_Status.DoorOpen | Door offline/invalid 정책 연계 | TBD (Signal Cache 설계) | CAN | Body_Status.DoorOpen | 0x200 | CLUSTER, PC_TOOL | 100 ms cyclic (uploaded Matrix) | CAN Cyclic | N/A | TBD / Review | DOOR_ECU_OFFLINE policy 연계 | Gateway | Gateway + Door/LIN + Cluster/PC | TBD | LIN response + CAN decode + Cluster/PC 표시 | HB 8.4~8.5 / current Matrix | 예시 행. 최신 DBC/LDF와 대조 후 실제 Route ID로 작성. | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
|  |  | LIN | [10 empty] | CAN | [14 empty] | ☐
Note on A6: Route ID 권장: RT-C2L-### 또는 RT-L2C-###
Note on B6: Draft → Review → Frozen. Blocked는 Interface 미결정 등으로 진행 불가한 경우.
Note on E6: 예: VCU_Command.Gear / Door_Status.DoorOpen
Note on J6: 예: Gear == R, valid source only, value changed 등. 근거 없는 조건 추가 금지.
Note on K6: Copy / Bool Copy / Enum→Bool / Enum Mapping / Scale / Range Check / Bitmask / Fault Map / Custom Function
Note on M6: Invalid, stale, timeout 시 해당 route 입력을 어떻게 취급할지. 미확정이면 TBD/OPEN으로 유지.
Note on N6: Signal Cache 구조 설계에서 실제 필드명을 확정. Routing 설계 초안에서는 TBD 가능.
Note on T6: LIN 출력이면 Schedule Slot 연계, CAN 출력이면 Cyclic/Event 정책 연계.
Note on W6: VCU_TIMEOUT, DOOR_ECU_OFFLINE, ALIVE_ERROR 등 관련 Fault/Health 정책 링크.
Note on Y6: CAN/LIN Interface 경계가 걸린 변경은 상대 담당자 리뷰 필요.
Note on AD6: 체크는 리뷰 완료를 의미하며 Merge만으로 Done 처리하지 않음.

## Interface_Ref
Interface Reference Snapshot
현재 업로드된 CAN_Matrix.xlsx / LIN_Matrix.xlsx에서 Gateway 관련 Interface를 추출한 참고 시트. 실제 최신 DBC/LDF와 불일치 시 최신 산출물을 우선합니다.
A. CAN Gateway-related Signals (imported reference)
Key | Message | CAN ID | Signal | Sender | Receiver | Period (ms) | Factor | Offset | Min | Max | Unit | Invalid | Definition Status | Review Status
VCU_Command.TorqueRequest | VCU_Command | ​0x100 | TorqueRequest | VCU | MOTOR, GATEWAY, CLUSTER | 10 | 0.1 | 0 | 0 | 4000 | Nm | ​0xFFFF | Confirmed | Review
VCU_Command.Gear | VCU_Command | ​0x100 | Gear | VCU | MOTOR, GATEWAY, CLUSTER | 10 | 1 | 0 | 0 | 5 | enum | 7 | Confirmed | Review
VCU_Command.Brake | VCU_Command | ​0x100 | Brake | VCU | MOTOR, GATEWAY, CLUSTER | 10 | 1 | 0 | 0 | 1 | bool | 1 | Confirmed | Review
VCU_Command.AliveCounter | VCU_Command | ​0x100 | AliveCounter | VCU | MOTOR, GATEWAY, CLUSTER | 10 | 1 | 0 | 0 | 15 | count | ​0xF | Confirmed | Review
Motor_Status.RPM | Motor_Status | ​0x110 | RPM | MOTOR | VCU, GATEWAY, CLUSTER | 10 | 1 | 0 | 0 | 12000 | rpm | ​0xFFFF | Confirmed | Review
Motor_Status.TorqueApplied | Motor_Status | ​0x110 | TorqueApplied | MOTOR | VCU, GATEWAY, CLUSTER | 10 | [6 empty] | OPEN | OPEN
Motor_Status.MotorState | Motor_Status | ​0x110 | MotorState | MOTOR | VCU, GATEWAY, CLUSTER | 10 | [6 empty] | OPEN | OPEN
Motor_Status.AliveCounter | Motor_Status | ​0x110 | AliveCounter | MOTOR | VCU, GATEWAY, CLUSTER | 10 | [6 empty] | OPEN | OPEN
Vehicle_Status.Speed | Vehicle_Status | ​0x120 | Speed | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Vehicle_Status.RPM | Vehicle_Status | ​0x120 | RPM | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Vehicle_Status.Gear | Vehicle_Status | ​0x120 | Gear | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Vehicle_Status.Brake | Vehicle_Status | ​0x120 | Brake | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Vehicle_Status.NetworkState | Vehicle_Status | ​0x120 | NetworkState | GATEWAY | CLUSTER, PC_TOOL | 20 | [6 empty] | OPEN | OPEN
Body_Status.ReverseLamp | Body_Status | ​0x200 | ReverseLamp | GATEWAY | CLUSTER, PC_TOOL | 100 | 1 | 0 | 0 | 1 | bool | 1 | Confirmed | Review
Body_Status.DoorOpen | Body_Status | ​0x200 | DoorOpen | GATEWAY | CLUSTER, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Body_Status.LightStatus | Body_Status | ​0x200 | LightStatus | GATEWAY | CLUSTER, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Body_Status.WindowStatus | Body_Status | ​0x200 | WindowStatus | GATEWAY | CLUSTER, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Gateway_Status.GatewayAlive | Gateway_Status | ​0x300 | GatewayAlive | GATEWAY | ALL CAN NODES, PC_TOOL | 100 | 1 | 0 | 0 | 15 | count | ​0xF | Confirmed | Review
Gateway_Status.GatewayHealth | Gateway_Status | ​0x300 | GatewayHealth | GATEWAY | ALL CAN NODES, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Gateway_Status.QueueUsage | Gateway_Status | ​0x300 | QueueUsage | GATEWAY | ALL CAN NODES, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Gateway_Status.SystemState | Gateway_Status | ​0x300 | SystemState | GATEWAY | ALL CAN NODES, PC_TOOL | 100 | [6 empty] | OPEN | OPEN
Fault_Status.FaultCode | Fault_Status | ​0x310 | FaultCode | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultSource | Fault_Status | ​0x310 | FaultSource | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultSeverity | Fault_Status | ​0x310 | FaultSeverity | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultState | Fault_Status | ​0x310 | FaultState | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultRecovery | Fault_Status | ​0x310 | FaultRecovery | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
Fault_Status.FaultMultiFault | Fault_Status | ​0x310 | FaultMultiFault | GATEWAY | CLUSTER, PC_TOOL | [7 empty] | OPEN | OPEN
B. LIN Gateway-related Signals (imported reference)
Key | Frame | PID | Signal | Publisher | Subscriber | Period (ms) | Factor | Offset | Min | Max | Unit | Invalid | Status | Review Needed
Door_Status.DoorOpen | Door_Status | 0x10 | DoorOpen | Door ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Door_Status.DoorLocked | Door_Status | 0x10 | DoorLocked | Door ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Door_Status.DoorAlive | Door_Status | 0x10 | DoorAlive | Door ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Door_Command.LockCommand | Door_Command | 0x11 | LockCommand | Gateway ECU | Door ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Door_Command.RequestState | Door_Command | 0x11 | RequestState | Gateway ECU | Door ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.HeadLamp | Light_Command | 0x12 | HeadLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.TurnLamp | Light_Command | 0x12 | TurnLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.HazardLamp | Light_Command | 0x12 | HazardLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.ReverseLamp | Light_Command | 0x12 | ReverseLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Command.BrakeLamp | Light_Command | 0x12 | BrakeLamp | Gateway ECU | Light ECU | 50 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Status.LampState | Light_Status | 0x13 | LampState | Light ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Status.LightAlive | Light_Status | 0x13 | LightAlive | Light ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Light_Status.DiagnosticState | Light_Status | 0x13 | DiagnosticState | Light ECU | Gateway ECU | 100 | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | HANDBOOK FIXED | 상대 담당자 리뷰 필요
Window_Command.TBD / OPEN | Window_Command | TBD / OPEN | TBD / OPEN | Gateway ECU | Window ECU | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | 상대 담당자 리뷰 필요
Window_Status.TBD / OPEN | Window_Status | TBD / OPEN | TBD / OPEN | Window ECU | Gateway ECU | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | TBD / OPEN | 상대 담당자 리뷰 필요
C. LIN Schedule Snapshot (imported reference)
Schedule ID | Cycle / Set | Slot Time (ms) | Entry | Frame Name | PID | Direction / Header | Master Action | Expected Response / Effect | Period Reference | Status | Review Needed | Owner / Reviewer | Source / Basis | Notes
LS-001 | BASE-20ms | 0 | 1 | Door_Status | 0x10 | Gateway Header -> Door; Door Response -> Gateway | Poll Door_Status | DoorOpen, DoorLocked, DoorAlive response | 100 ms frame / 20 ms base slot | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common + Door | Handbook v1.0 §6.2–6.3 (p.18–19) | First slot in the fixed baseline schedule.
LS-002 | BASE-20ms | 20 | 2 | Light_Command | 0x12 | Gateway -> Light | Publish Light_Command | Light ECU accepts Head/Turn/Hazard/Reverse/Brake command | 50 ms frame / 20 ms base slot | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common + Light | Handbook v1.0 §6.2–6.3 (p.18–19) | Second slot in the fixed baseline schedule.
LS-003 | BASE-20ms | 40 | 3 | Light_Status | 0x13 | Gateway Header -> Light; Light Response -> Gateway | Poll Light_Status | LampState, LightAlive, DiagnosticState response | 100 ms frame / 20 ms base slot | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common + Light | Handbook v1.0 §6.2–6.3 (p.18–19) | Third slot in the fixed baseline schedule.
LS-004 | BASE-20ms | 60 | 4 | Door_Command | 0x11 | Gateway -> Door | Publish Door_Command | Door ECU accepts LockCommand / RequestState | 100 ms frame / 20 ms base slot | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common + Door | Handbook v1.0 §6.2–6.3 (p.18–19) | Fourth slot in the fixed baseline schedule.
LS-005 | BASE-20ms | 100 | repeat | Schedule 0 repeat | n.a. | Gateway Master timing | Repeat from t=0 | 100 ms repeat boundary; 20 ms base schedule continues | 100 ms repeat | HANDBOOK FIXED | 상대 담당자 리뷰 필요 | Gateway + LIN Common | Handbook v1.0 §6.2–6.3 (p.18–19) | Repeat marker; not a LIN frame PID.
LS-006 | WINDOW-EXT | TBD / OPEN | TBD / OPEN | Window_Command | TBD / OPEN | Gateway -> Window | Window command slot TBD / OPEN | Window ECU accepts UP/DOWN command; detailed response/data TBD / OPEN | TBD / OPEN | TBD / OPEN | 상대 담당자 리뷰 필요 | Gateway + Window + Test | System Architecture Spec v1.0 §8.2–8.3 (p.16); §12 OPN-07 (p.21) | Do not assign a fixed slot before Window interface review.
LS-007 | WINDOW-EXT | TBD / OPEN | TBD / OPEN | Window_Status | TBD / OPEN | Window -> Gateway | Window status response slot TBD / OPEN | Limit/status response; detailed response/data TBD / OPEN | TBD / OPEN | TBD / OPEN | 상대 담당자 리뷰 필요 | Gateway + Window + Test | System Architecture Spec v1.0 §8.2–8.3 (p.16); §12 OPN-07/08 (p.21) | Window offline threshold and recovery policy are also TBD / OPEN.

## Change_Log
Routing Change Log
Routing 규칙 변경 및 Interface 영향 추적. CAN/LIN Interface 변경은 상대 담당자 리뷰 필요.
Routing / Interface Change Control
Change ID | Date | Jira / Issue | Route ID | Target | Old Definition | New Definition | Reason / Decision | Affected ECU / Team | Author | Counterpart Reviewer | Status | Evidence / Link | Remark
RT-INIT-001 | 2026-10-01 | TBD | C2L-001~007 | CAN→LIN Routing initial population | Template example only | 2 routable paths + 5 interface gaps identified | Populate routing based on current CAN Matrix and latest message definition Team Encoding | VCU / Gateway / Light / Door / Window / CAN / LIN | Gateway | 상대 담당자 리뷰 필요 | Review | CAN_Matrix.xlsx; 메시지 정의서_v0.3_점검완료.xlsx | vehicle.dbc / vehicle.ldf 최신본과 대조 후 Freeze. Merge != Done.
RT-REV-002 | 2026-10-01 | TBD | C2L-001~007 | CAN→LIN Routing technical review | v0.2 | v0.3 Reviewed | Gear reserved handling correction; Brake invalid conflict flagged; LIN baseline/PID ambiguity noted; blocked source gaps retained | VCU / Gateway / CAN / LIN / Door / Light / Window | Gateway | 상대 담당자 리뷰 필요 | Review | CAN_Matrix.xlsx; LIN_Matrix.xlsx; 메시지 정의서_v0.3; 기능 정의서; Handbook/ARCH | Freeze blocker는 Review_Summary 참조.
RT-DEC-002 | 2026-10-01 | TBD | C2L-001~007 | v0.4 CAN→LIN design decisions | v0.3 review blockers/open items | Body command source/bit allocation/fallback/validity/schedule baseline decided | Create decision baseline and required interface changes; keep official freeze pending reviews/artifact sync | VCU / Gateway / CAN / LIN / Door / Light / Window | Gateway | 상대 담당자 리뷰 필요 | Review | CAN_Matrix.xlsx; 메시지 정의서_v0.3; 기능 정의서; Handbook/Architecture | Design decision complete; official Interface Freeze pending DBC/LDF + counterpart review.